## Sheet1
Task Name | Duration | Start | Predecessors
Requirement Analysis | 3 weeks | 2025-01-06
System Design | 4 weeks |  | 1
Database Design | 2 weeks |  | 1
Frontend Development | 5 weeks |  | 2
Backend Development | 6 weeks |  | 2,3
Integration Testing | 3 weeks |  | 4,5
User Acceptance Testing | 2 weeks |  | 6
Deployment | 1 week |  | 7