## Sheet1
BAC (Budget at Completion) | 18000
PV (Planned Value) | 9000
EV (Earned Value) | 7200
AC (Actual Cost) | 8500 |  | sakshi sapkota
Metric | Formula | calculation | result | interpretation
SV (Schedule Variance) | EV - PV | -1800 | -1800 | Behind Schedule
SPI (Schedule Performance Index) | EV / PV | 0.8 | 0.8 | 80% efficiency
CV (Cost Variance) | EV - AC | -1300 | -1300 | Over Budget
CPI (Cost Performance Index) | EV / AC | 0.84706 | 0.847 | Cost Overrun
EAC (Estimate at Completion) | BAC / CPI | 21250 | 21251 | Revised total cost
VAC (Variance at Completion) | BAC - EAC | -3250 | -3251 | Expected overrun
Month | PV | EV | AC
1 | 1500 | 1000 | 1200
2 | 3000 | 2200 | 2600
3 | 4800 | 3500 | 4100
4 | 6500 | 4800 | 5700
5 | 8000 | 6200 | 7300
6 | 9000 | 7200 | 8500